## Work to import
Programmed work to import into a work plan
One row per project. Asset ID, Treatment and Year are required; see the next sheet for how to fill each column.
Asset ID | Treatment | Year | Programmed Year | Build Year | Cost | Status | Funding | Notes
WL-0225 | Replacement | 2026 |  | 2027 | 1165000 | In Progress | Capital Improvement Program | CIP-2026-001 · condition 2
WL-0073 | Replacement | 2026 |  | 2027 |  | Approved | Road reconstruction (dig once) | CIP-2026-002 · condition 4
WL-0155 | Rehabilitation | 2026 |  | 2027 |  | In Progress | State revolving fund | CIP-2026-003 · condition 35
WL-0105 | Rehabilitation | 2026 |  | 2027 |  | Approved | Capital Improvement Program | CIP-2026-004 · condition 37
WL-0219 | Dig-once repair | 2026 |  |  | 30000 | In Progress | Road reconstruction (dig once) | CIP-2026-005 · condition 55
WL-0090 | Lining | 2026 |  |  |  | Approved | State revolving fund | CIP-2026-006 · condition 55
WL-0252 | Replacement | 2027 | 2026 | 2028 |  | Approved | Capital Improvement Program | CIP-2027-001 · condition 5
WL-0229 | Replacement | 2027 | 2026 | 2028 |  | Approved | Road reconstruction (dig once) | CIP-2027-002 · condition 6
WL-0132 | Rehabilitation | 2027 | 2026 | 2028 | 290000 | Approved | State revolving fund | CIP-2027-003 · condition 37
WL-0258 | Rehabilitation | 2027 | 2026 | 2028 |  | Approved | Capital Improvement Program | CIP-2027-004 · condition 38
WL-0200 | Dig-once repair | 2027 |  |  |  | Approved | Road reconstruction (dig once) | CIP-2027-005 · condition 56
WL-0045 | Lining | 2027 |  |  |  | Approved | State revolving fund | CIP-2027-006 · condition 56
WL-0026 | Replacement | 2028 | 2027 | 2029 | 425000 | Planned | Capital Improvement Program | CIP-2028-001 · condition 7
WL-0190 | Replacement | 2028 | 2027 | 2029 |  | Planned | Road reconstruction (dig once) | CIP-2028-002 · condition 7
WL-0193 | Rehabilitation | 2028 | 2027 | 2029 |  | Planned | State revolving fund | CIP-2028-003 · condition 38
WL-0206 | Rehabilitation | 2028 | 2027 | 2029 |  | Planned | Capital Improvement Program | CIP-2028-004 · condition 38
WL-0166 | Dig-once repair | 2028 |  |  | 30000 | Planned | Road reconstruction (dig once) | CIP-2028-005 · condition 56
WL-0137 | Lining | 2028 |  |  |  | Planned | State revolving fund | CIP-2028-006 · condition 56
WL-0227 | Replacement | 2029 | 2028 | 2030 |  | Planned | Capital Improvement Program | CIP-2029-001 · condition 8
WL-0064 | Replacement | 2029 | 2028 | 2030 |  | Planned | Road reconstruction (dig once) | CIP-2029-002 · condition 8
WL-0107 | Rehabilitation | 2029 | 2028 | 2030 | 465000 | Planned | State revolving fund | CIP-2029-003 · condition 38
WL-0247 | Rehabilitation | 2029 | 2028 | 2030 |  | Planned | Capital Improvement Program | CIP-2029-004 · condition 38
WL-0127 | Spot Repair | 2029 |  |  |  | Planned | Road reconstruction (dig once) | CIP-2029-005 · condition 57
WL-0145 | Lining | 2029 |  |  |  | Planned | State revolving fund | CIP-2029-006 · condition 57
WL-0098 | Replacement | 2030 | 2029 | 2031 | 930000 | Planned | Capital Improvement Program | CIP-2030-001 · condition 8
WL-0164 | Replacement | 2030 | 2029 | 2031 |  | Planned | Road reconstruction (dig once) | CIP-2030-002 · condition 9
WL-0253 | Rehabilitation | 2030 | 2029 | 2031 |  | Planned | State revolving fund | CIP-2030-003 · condition 39
WL-0062 | Rehabilitation | 2030 | 2029 | 2031 |  | Planned | Capital Improvement Program | CIP-2030-004 · condition 39
WL-0099 | Lining | 2030 |  |  | 290000 | Planned | Road reconstruction (dig once) | CIP-2030-005 · condition 57
WL-0250 | Lining | 2030 |  |  |  | Planned | State revolving fund | CIP-2030-006 · condition 57
WL-9999 | Spot Repair | 2027 | [5 empty] | Mistake: no such segment
WL-0225 | Pipe Bursting | 2028 | [5 empty] | Mistake: not in the treatment library
WL-0073 | Spot Repair | 2034 | [5 empty] | Mistake: outside a 2026–2030 plan
WL-0155 | Spot Repair | 2029 |  |  | TBD |  |  | Mistake: cost is not an amount
WL-0105 | Replacement | 2027 | 2029 |  |  |  |  | Mistake: programmed after the year it is paid for

## How to fill it in
How to fill in each column
Every row is checked before anything is imported, and nothing is written while any row has an error.
Column | Required | What to put | Example
Asset ID | Yes | The segment's asset ID. It must be an active segment. | WL-0058
Treatment | Yes | A treatment or a treatment combination, spelled as in the library (see the Treatments sheet). A combination imports as one project. Anything not in the library must be created in Settings first. | Dig-once repair
Year | Yes | The year the money is spent. It must fall inside the plan. Without the two columns below, it is also the year the work is decided and built. | 2027
Programmed Year | No | The year the work was decided or committed — no later than Year. Blank means the same as Year. A scenario that locks this plan's work leaves the segment alone from this year until the Build Year. | 2026
Build Year | No | The year the work is built and the segment's condition changes — no earlier than Year. Blank means the same as Year. | 2028
Cost | No | The project's total cost. Leave blank to price it from the treatment library. | 185000
Status | No | Planned, Approved, In Progress, Complete, Deferred or Cancelled. Blank means Planned. | Approved
Funding | No | Where the money comes from. Blank means Imported. | Road scheme
Notes | No | Anything to keep with the project, such as a project number. It is shown in the reasons. | CIP-2027-014
Two rows on the same segment in the same year stay two projects — use a combination to make them one. Work already in the plan is kept; an exact repeat (same work, segment and year) is skipped.

## Treatments
Names the Treatment column accepts
13 treatments and 3 combinations in the library.
Name | Kind | Includes / category
Abandonment | Treatment | Retire
Cathodic Protection | Treatment | Rehabilitate
Coating | Treatment | Rehabilitate
Emergency Repair | Treatment | Repair
Inspection | Treatment | Assess
Leak Repair | Treatment | Repair
Lining | Treatment | Rehabilitate
Rehabilitation | Treatment | Rehabilitate
Relining | Treatment | Rehabilitate
Replacement | Treatment | Renew
Spot Repair | Treatment | Repair
Upsizing | Treatment | Renew
Valve Replacement | Treatment | Repair
Dig-once repair | Combination | Spot Repair + Valve Replacement
Restore and protect | Combination | Lining + Coating
Trenchless package | Combination | Relining + Cathodic Protection